Albury Wodonga     olunteer Resource Bureau Inc

# Final report and appendices

## Project

Know Your Gizmo

## Project Management

Albury Wodonga Volunteer Resource Bureau Inc

## Partners

Albury High School

Age Concern

## Location

Albury

The operation of the Australian Communications Consumer Action Network is made possible by funding provided by the Commonwealth of Australia under section 593 of the Telecommunications Act 1997. This funding is recovered from charges on telecommunications carriers.

ACCAN operates an annual grants scheme which provides up to $60,000 for each project that is selected for funding. Grants projects help empower communities to act in their own interests, help enable consumers to navigate the challenges of the communications market, and contribute to a sound body of evidence for consumer advocacy.

Australian Communications Consumer Action Network
Website: www.accan.org.au
Email: grants@accan.org.au
Telephone: 02 9288 4000
TTY: 02 9281 5322

Albury Wodonga Volunteer Resource Bureau
Website: www.vrb.org.au
Email: volunteercentre@vrb.org.au
Telephone: 02 6021 0990

This work is copyright, licensed under the Creative Commons Attribution 3.0 Australia Licence. You are free to cite, copy, communicate and adapt this work, so long as you attribute the authors and “Albury Wodonga Volunteer Resource Bureau, supported by a grant from the Australian Communications Consumer Action Network”. To view a copy of this license, visit http://creativecommons.org/licenses/by/3.0/au/

# Contents

Final report and appendices	1

Project	1

Project Management	1

Partners	1

Location	1

Contents	2

Project Description	4

The issue	4

Objectives	4

The partners	5

Evaluation	11

Impact	11

Students	11

Older participants	12

Partners	14

Community	14

Outcomes	16

Future Actions	18

Appendix 1	19

Students pre project	19

Appendix 2	21

Students mid project	21

Appendix 3	23

Students conclusion	23

Appendix 4	27

Older participants pre project	27

Appendix 5	31

Older participants mid project	31

Appendix 6	33

Older participants conclusion	33

Appendix 7	37

Staff/facilitator/teacher conclusion	37

# Project Description

## The issue

The Albury Wodonga Volunteer Resource Bureau engages with people from all age groups. Many young people seek an opportunity to volunteer however the projects available can be limiting and not meaningful for the young people. Older people that attend training often express their concerns and inability to understand or use new technologies including mobile phones, Facebook, internet, digital televisions, cameras, microwaves, GPS’s and even changing radio stations in their cars.

Fear of new technology can limit one’s ability to maintain family contact and be informed about current affairs and local events. Rapid changes in technology make it difficult for some older members of the community to understand how to operate new appliances e.g. how to record programs on a DVD recorder.

A successful pilot project run two years ago demonstrated that facilitating a link between groups of young people and older people with concerns about their use of technology could be both informative and socially worthwhile.

Many enquiries had been made since that project indicating that there were adequate numbers of older people interested in such a project.

Albury High School wished to engage young people in the community in a volunteering capacity. Over the years the school had expressed an interest in becoming involved in a suitable project.

## Objectives

- AWVRB aimed to train twenty Year 10 volunteers from Albury High School in the skills needed for volunteering and communicating with older people.

- Older people from the community would be sourced through media coverage and flyers.

- Older people would work with High School students for 8 weeks for one hour/week.

- Older people would take whatever “gizmo” or “gizmos” they already owned and learn how to use them thereby increasing their confidence and assisting them to remain up to date with new technologies, possibly leading to improving their communication skills and re-engaging with family.

- With greater knowledge and skills older participants would have an opportunity to advocate for other consumers on the use of the product.

- Additional aspects of the project would be developing awareness of the role of broadband, discussing the use of technology in emergency situations e.g. bushfire and security issues that arise with the use of technology.  These would be addressed by inviting guest speakers with expertise in those areas.

- Research on the issues that challenge the participants would be recorded and used for feedback.

## The partners

Key personnel involved in this project were the manager of the AWVRB, the CEO of Age Concern and a teacher from Albury High School. The team worked together to support this project “Know Your Gizmo”.

Additional team members were added through the course of the project to ensure that adequate numbers of ‘helpers’ were available at each session.  These included at various times, the accompanying teacher from Albury High School, 4 staff members from AWVRB and a placement student and a volunteer attached to AWVRB.

| Date | Activity outline | Activity details if required | Who is responsible/involved | Comments |
| --- | --- | --- | --- | --- |
| 02/12 & 03/12 | Initial meetings with staff/potential partners to discuss project Create work plan according to project application |  | Jemma Vik Teacher Heather | Completed |
| 03/12 | Write submission and get agreement from partners re roles |  | Jemma Vik Teacher Heather | Completed |
| 03/12 | Submit application |  | Jemma Heather | Completed |
| 04/12 | Speak with stakeholders re success of submission |  | Jemma Vik teacher | Application successful: 08.06.12 ACCAN media release 20.06.12 Completed |
| 06/12 | Create MOU with all stakeholders |  | Jemma Vik teacher Heather | Completed |
| 03/12 | Provisional booking rooms/ training with organisations etc |  | Jemma Jodie Vik | Completed |
| 07/12 | Purchase laptops, iPads and broadband USBs |  |  | 2 laptops and 2 ipads purchased |
| Date | Activity outline | Activity details if required | Who is responsible/involved | Comments |
| 07/12 | Advertise the project/registrations | Distributed flyers to community centres, libraries and other suitable locations where target group like to see them Contacted local newspaper – Border Mail Radio spot ABC local radio – Jemma Toohey spoke with Gaye Pattison Radio spot 2AY WIN TV News attended first session of Know Your Gizmo – filmed activities and on local WIN news 31.07.12 Take registrations by phone and list | Jemma Lindee Heather | Border Mail article and photo 25.07.12 Large increase in interest as a result of newspaper article Survey conducted at first session rather than mailed WIN news coverage 31.07.12 |
| 07/12 09/12 | Training students | Sessions 1, 2. Induction to volunteering and AWVRB Consent forms – to be signed by parents/guardians Communicating with Older People and listening skills Privacy & confidentiality Older participants to be asked to contribute a gold coin at each session to be donated to a charity of choice by the students. Student survey: Perceptions of selves as volunteers and in technology use Survey current technology use & expectations from project | Jemma AHS teacher AHS Students | 14 Students enthusiastic and interested Some students take home ipads for research and to learn how to use them Survey completed and collated Students voted on charity to receive donated money – from Country Hope, MS Australia and YES Youth and Family Services Decision to donate to Country Hope. |
| Date | Activity outline | Activity details if required | Who is responsible/involved | Comments |
| 07/12-09/12 | Supporting older people | Session 3:Two groups meet – meet and greet, get to know one another activities. Create relaxed atmosphere Older people sign consent forms – photos etc Purpose of project explained Students look at range of devices – decide where they best fit Older people not locked into one device for whole project Let students know technology available for research at training venue Practical - partnerships formed and young people simply & slowly impart knowledge and allow older people to practise Develop awareness of learning styles e.g. need for written directions, step by step & need to check for understanding Sessions 4,5,6,7,8, 9: Each session – welcome – discuss latest needs. Technology in emergency situations--guest speaker Safety issues with internet: guest speaker Local Police | Jemma AHS teacher & students Older people | 10 A H students A H teacher 33 older people 5 VRB staff Large numbers so worked in 3 different areas, the learners were allocated according to their particular Gizmo. We didn’t follow the original plan – just allocated places, had people sign in, complete surveys and consent forms and straight onto Gizmos. (** some chose not to sign consent form) Total of 8 sessions with both students & older people Basic info about personal detail security and cyber bullying for younger people. |
| Date | Activity outline | Activity details if required | Who is responsible/involved | Comments |
| 06/12-09/12 | Gathering data & submitting as required to all stakeholders | Data gathered throughout duration of project Pre project survey of expectations - students and older participants Mid project attitudes to project – student and older participants Conclusion of project – survey of comments about project plan, methods used, facilities, changes in attitudes, impressions, suggested improvements – students, older participants, staff | Jemma AHS teacher Heather | Pre project surveys of students and older participants – results collated 28.08.12 Mid project surveys of students and – results collated Photographic records Ongoing reports by email and phone to ACCAN Anecdotal comments from phone class, chats with participants |
| 06/12-09/12 | Send invitations for celebration and feedback sessions |  | Jemma Lindee Heather | 10.09.12-14.09.12 |
| 09/12 | Celebrations gathering of evidence | Session 10. Final evaluation and celebration – afternoon tea. | Jemma Lindee Heather | 18.09.12 Visit by Narelle Clarke and Erin Turner of ACCAN Afternoon tea Cheque $300 given to students for donation to Country Hope End of project surveys of students, older participants - results collated |
| Date | Activity outline | Activity details if required | Who is responsible/involved | Comments |
| 09/12 | Lessons learnt shared with all stakeholders |  | Jemma AHS teacher Heather |  |
| 09/12 | Final Report submitted |  | Jemma Heather |  |

# Evaluation

## Impact

On Tuesday afternoons there was a happy buzz in the rooms of Age Concern in Albury when the Albury High School students and the older participants met for an hour to demystify ‘gizmos’.  All participants sat in groups of 2, 3 or 4 with a student assisting or at tables (for the laptop group). There was a great spirit in the room as people learnt something new and shared it with another participant.

### Students

During training the Albury High School students were positive, involved and said that they enjoyed the activities.  At the conclusion of the project the students put their names down to participate if the project were to continue next term.

Pre project, 73% of the students had previously volunteered in some form and 82% of them had helped older people with technology at some time.  Eighty two percent also expected the project to be fun, whilst 64% expected it to be easy.  When asked how they felt about the project, 55% said they are happy and 92% were interested. (Students could choose multiple faces expressing emotions see Appendix 1).

Comments made include:

Volunteering sounds interesting no matter what you’re doing and also fun.

Seems interesting and potentially fun.  It will help me reach my goal of an exchange.

Mid way through the project, 86% of the students felt happy and 64% were interested. (students could choose multiple faces expressing emotions see Appendix 2).  A hundred percent felt that the project was meeting their expectations.

Comments about the highlights include:

Helping people save their money

Learning and teaching how to use computers, iphones and ipads.

Just connecting with people and helping them with their problems

The pride you receive from helping people with everyday objects

At the conclusion of the project 100% of students surveyed said they felt “great” about volunteering as part of “Know Your Gizmo” and that they would volunteer again in this type of project. They would also recommend this type of volunteering to other students. 100% of the students also felt that their efforts were appreciated.

Some comments:

All elder participants helped all of us feel like our opinion was valued.

All of the people I helped were very appreciative and I saved a few a lot of money.

Asked to comment on the experience of working with older people, students’ comments were positive and in summary, expressed the fact that they enjoyed meeting new people, it had been easy to teach new skills and the people they had worked with had been “nice” and “lovely”. (See Appendix 3)

Some comments:

Got to meet different people and helped me learn how to teach and be patient.  Overall had a great time.

...it was really good.  I think that it really improved my socialisation and conversational skills with older adults. Yes I found it easy – you have to speak slowly and simply.

The people I assisted were very good at understanding and very lovely.

### Older participants

Pre project, 69% said their reason for participating was to learn how to use a specific piece of technology, 18% expressed a wish to keep up with technology or a general interest and a small number said this would help them make a decision about purchasing new technology. (See Appendix 4)

In response to the question: “What are your feelings about learning how to use new technology?”, 34% of the participants expressed concern.

Graph 1.

The general feeling throughout this project was one of warmth and enjoyment as expressed in the mid project surveys of older participants and students.  Ninety four percent of the older participants felt happy about the project and 100% were interested and felt that it was meeting their expectations. (See appendix 5)

Some comments made when asked about a highlight of the project at that stage were:

Getting answers to my questions

Learnt to clear apps, put on internet and download

Skype and Facebook registration

Didn’t matter if you didn’t know anything – made welcome

At the conclusion of the project, 100% of the participants surveyed said they had learnt what they wanted and that they were using their ‘gizmos’ more effectively. Ninety four percent said that there had been a change in their level of confidence regarding technology. (See Appendix 6)

Eighty nine percent of participants also expressed greater confidence in their ability to make decisions about and purchase new technology.

Pre the project, 30% of those surveyed had thrown away, given away or just not used a ‘gizmo’ they owned.  When asked whether they were given adequate instructions when purchasing their gizmos, 82% felt that they hadn’t.

The attitudes of the older participants to the students were positive throughout the project as shown by staff responses, “A positive experience resulting from the willingness of participants to share interests in new technologies” and “Interacted well – even on final day (celebration afternoon tea) students were sitting and chatting to the people they worked with.”

The happy and productive atmosphere of the sessions is reflected in the responses from the older participants in response to the question, “How was the experience of working with the young students?”

Yes, the students coped very well with a lack of knowledge and endless questions.  They were friendly, pleasant, tolerant and very knowledgeable about the ipad.

Yes, really enjoyed the students’ commitment, help and knowledge.

What a lovely group of students.  Very polite and happy to help.

Attendance: Over the course of the project 48 older people attended an average of 3.3 sessions each. Fourteen people attended only one session whereas 20 people attended two, three or four sessions. The average daily attendance was 20 people.

Flexibility of attendance appealed to the participants who were free to move on once they felt confident with a particular gizmo or could bring along another gizmo when they felt confident with the first.

### Partners

Initially there was a limited response to the media coverage of the planned project then as a result of a newspaper article and photo in the Border Mail, requests for inclusion in the project came in very quickly.  The majority of participants who were surveyed noted that they had heard about the project through the newspaper article.

Because of the large numbers of older participants attending the initial sessions, all available AWVRB staff as well as a placement student and a volunteer assisted with management and tutoring in the use of ‘gizmos’.

### Community

The participants in this project came from a section of the community that is not usually represented in training offered by AWVRB.  From observation, the ages of “older” participants would have ranged from 50 years to 80+.  With the high proportion of participants wanting help with ipads, it might be assumed that these were people who had an interest in keeping up with changes in technology as well as the financial ability to do so.

Many of the participants mentioned the project to friends who wanted to join the group and a waiting list was formed by AWVRB.  Some people on the waiting list were able to join the project in later sessions.

By drawing from this section of the community, AWVRB and Age Concern had an opportunity to showcase their services and the Age Concern facilities and the skills of the Albury High School students were recognised by a larger part of the community.

Some participants spoke of this project to friends who lived in other areas and they expressed a wish that something similar could be arranged.

  - Strengths of approach to tackling the issue

This approach was most effective for the students, the older participants and for the AWVRB and Age Concern.

  - What would you do differently if you were to start again and why?

We would maintain the same structure if we were to conduct a similar project.

When surveyed at the conclusion of the project, 50% of the students felt that the project didn’t need any improvements.  25% felt that it could have been improved with the involvement of more students.

All the older participants surveyed at the conclusion to the project were happy with the informal student tutoring system and they did not feel that any significant improvements were required. A typical comment was:

One to one attention appreciated.  Questions that I asked were answered.

A suggestion worth consideration was that the one student work with the same older participant for the duration of the project as “Different students explain things in a different way which can be confusing”.

Another concern expressed by an older participant was lack of knowledge of what she needed to know or what her gizmo was actually capable of.  This may suggest that it would be worth adding a component of demonstration to future projects, in which groups interested in particular gizmos such as ipads might be given an overall picture of the main uses of that item.

The most common request from the older participants was that the project could continue to run at various places and times through the year.

Some modifications would be:

Limit numbers to no more than two older participants to one student.

Ensure facilities included adequate rooms and furniture to accommodate people needing a table for laptops.

Additional guest speakers

Guest speaker who can give independent advice to questions about the most suitable devices for particular needs – e.g. Do I need an ipad?  Will it meet my needs?

The most effective media coverage for the target group was the newspaper article and photo in the Border Mail.

# Outcomes

| Objectives | Goals successfully met |
| --- | --- |
| AWVRB aimed to train twenty Year 10 volunteers from Albury High School in the skills needed for volunteering and communicating with older people. This would give the young people an opportunity to volunteer in a meaningful way, using their skills and knowledge of technology to assist older people with their gizmos. | Fourteen Year 10 volunteers from Albury High School were trained in the skills required for volunteering and communicating with older people. As previously mentioned in this report, the students felt that their efforts were much appreciated by the older participants. |
| Older people from the community would be sourced through media coverage and flyers. | The target of 30 older people was exceeded, with 48 attending at least one session of “Know Your Gizmo” and another 16 on the waiting list or expressing interest in future training. |
| Older people would work with High School students for 6 weeks for one hour/week. | The students and older participants worked together for 8 weeks, for one hour per week. |
| Older people would take whatever “gizmo” or “gizmos” they already owned and learn how to use them thereby increasing their confidence and assisting them to remain up to date with new technologies, possibly leading to improving their communication skills and re-engaging with family. | In the pre project survey, 45 older participants expressed an interest in learning how to use a wide variety of ‘gizmos’. Further details about their expressed interests are shown in Tables 1 and 2. |
| With greater knowledge and skills older participants would have an opportunity to advocate for other consumers on the use of the product. | This is difficult to measure as outcomes are long term. Participants have been positive and vocal in their praise for the project, enhancing the reputation of AWVRB and the Albury High School students. |
| Additional aspects of the project would be developing awareness of the role of broadband, discussing the use of technology in emergency situations e.g. bushfire and security issues that arise with the use of technology. These would be addressed by inviting guest speakers with expertise in those areas. | A policewoman with expertise in technology security spoke with the group, targeting personal detail security and cyber bullying. |
| Research on the issues that challenge the participants would be recorded and used for feedback. | This report records the challenges experienced by participants. |

Graph 2.

In the survey at the conclusion of the project, completed by 18 participants in response to the question, “Which gizmos have you had help with during the project?” the response is as shown in the table below.  Variations between the pre project interest and the concluding survey can be accounted for by the fact that the composition of the group had changed considerably as some left and new participants joined. Despite this, the dominant need was for help with phones, ipads, laptops and cameras.

Graph 3.

In the final survey students and staff were asked what the most common problems were that they helped solve.  (See Appendices 3 and 7)

The list includes:

using touch screens

using new applications

understanding and remembering processes

not reading or understanding manuals

emails: setting up accounts, sending photos,

texting

setting up contacts lists

organising photos and photo editing

file management

There has been a sense of elation throughout this project because the learners were enthusiastic and committed to gaining new skills and there was a great spirit of camaraderie between them.

# Future Actions

Now that this project has been successfully run we can share the plan and templates with other organisations that wish to run a similar project.

# Appendix 1

## Students pre project

Albury Wodonga Volunteer Resource Bureau

Student Survey

Pre volunteering

11 responses

17.07.2012

- Have you volunteered before?

Yes : 8  No: 3

If yes, where and what did you do?

- Sports volunteering with Albury Public School, Coach U11 soccer team with my brother.

- Helping young kids with sport

- Carevan

- 2 x Cleaning up school garden

- ANZAC Day token appeal & Remembrance Day, defence marches

- 2 x Aged Care Home

- Have you ever helped older people – grandparents, neighbours with technology e.g. how to record a TV program?

Yes: 9   No: 2

- My Pop

- Parents use computer and everything to do with technology

- My family

- Yeah – grandparents

- Grandma

- What do you expect this experience to be like?

- I expect it to be more useful and more fun with them and also myself.\

9 x fun

0 x boring

6 x exciting

7 x easy

0 x stressful

1 x difficult

1 x interesting

- So far, how are you feeling about this project?

Circle the face or faces that show how you feel.

Bored	             6 x Happy	            Exhausted               Disappointed        10 x Interested

- Any other comments?

- Volunteering sounds interesting and I am really excited to do it.

- I hope it will be fun if they feel more confident with us and also ourselves.

- Volunteering sounds interesting no matter what you’re doing and also fun.

- Seems interesting and potentially fun.  It will help me reach my goal of an exchange.

# Appendix 2

## Students mid project

Collated results of mid project evaluation

28.08.12

Albury High students:  14 responses

- So far, how are you feeling about this project?

Circle the face or faces that show how you feel.

0 x Bored	 12 x Happy	         0 x Exhausted                    0 x Disappointed       9 x Interested

- Is this project meeting your expectations?

14 x Yes

Additional comment: Very much so

- A highlight so far?

- Helping people to save their money

- Learning and teaching how to use computers, iphones and ipads

- Teaching others and to myself how to use iphones and ipads

- Teaching to use ipads and iphones and having lots of fun

- Meeting and being able to help people

- Helping people

- Helping people to understand technology

- Just connecting with people and helping them with their problems

- Meeting people

- Being able to teach a very nice lady

- Getting along with older people

- The pride you receive from helping people use everyday objects

- Being told that you’ve helped someone

- The fun and interesting talks, helping with technology

- Any disappointments?

13 x No

Additional comments:

- Not being able to help

- Not at all

- So far it’s been really good

- Any other comments or suggestions?

- Not really – I’m really enjoying

- It’s really enjoyable

- I think it’s a great program and good to give back to the community, meet new people and help them with their problems. Very happy and fulfilling!

- Wish could do this for the rest of the term and it is great fun

- Maybe next time promoting the program to have more people coming!

# Appendix 3

## Students conclusion

Albury Wodonga Volunteer Resource Bureau

Collated results

11 students present (18th Sept, 2012) 11 responses

Albury High student survey – conclusion of project

To help us with our reporting to ACCAN the funding body that enabled this project to go ahead, please complete this survey.

| How did you feel about volunteering as part of this project? 11 x Great Good OK Not so good Didn’t like it |
| --- |
| Would you volunteer in this sort of project again? | 11 x YES | 0 x NO |
| Would you recommend this sort of volunteering to other students? | 11 x YES | 0 x NO |
| How was the experience of working with older people? e.g. Did you get to know some people? Did you find it easy/difficult to help them with their gizmos? Did you have to go very slowly? Comments: It was fairly easy. I just had to explain in not so technical way. It was great to meet new people in the community. And the people I worked with worked very well and very fast. It was lovely working with older people. I did get to know a few people and it was really nice. I found it easy to explain. Easy to teach people and got to know some people. Didn’t have to go too slowly. Yeah it was really good. I think that it really improved my socialisation and conversational skills with older adults. Yes I found it easy – you do have to speak slowly and simply. Got to meet different people and helped me learn how to teach and be patient. Overall had a great time. I had a great time working with older people. They were pretty nice and I enjoyed a lot. I had fun with them and they were very co-operative. The people I assisted were very good at understanding and very lovely. It was easy and good – enjoyed each week. I found it easy and rewarding. |
| Did you feel that your volunteering efforts were appreciated? Comments: Yes x 10000 All elder participants helped all of us feel like our opinion was valued. All of the people I helped were very appreciative and I saved a few a lot of money. Enjoyed it a lot. Yes very – they appreciated it. | 11 x YES | NO |
| Which gizmos did you help with most? 6 x iPad 4 x laptops 4 x mobile Phones 3 x iphone Everything Computers Smart phones – (Samsung Galaxy II) ipod |

| Did you learn to use some gizmos that you hadn’t previously used? Comments: I can’t help someone to do something if I don’t know it. Yes I learnt a lot as well. I taught myself how to use ipad as I taught them (other people). I learnt many things and taught many things. I had a good experience. | 7 x YES | 4 x NO |
| --- | --- | --- |
| Were the facilities suitable? Comments: Facilities were perfect Great! | 11 x YES | 0 x NO |
| Was the timing of sessions suitable? Length of each session? Number of sessions altogether? Comments: I think it all ran very smoothly every time. | 11 x YES 11 x YES 11 x YES | 0 x NO 0 x NO 0 x NO |
| Were the numbers of students and participants suitable at all sessions? Comments: Some responded both yes and no, reflecting the changes in numbers over the duration of the project. Need more students for one on one ‘teaching’ We sometimes doubled up with participants but we weren’t spread thin Sometimes there were more students and sometimes there were more adults | 10 x YES | 3 x NO |

What were the main problems older people were experiencing with technology? Comments: Probably the touch screens The main problems were the basics such as emails, texts, organising contacts, sending picture messages. Internet, general instructions Just learning the basics that get what they want to do. Couldn’t remember some things so that made it hard for them. Of course to use new application which are new and hard for them. Just how to use apps and such. Not sending messages. Emails and photos To contact others with pictures That things were not explained to them properly and quite often they are taken advantage of by sales people (they give them the most expensive product and say it is the only option).

Do you think this was a suitable way to help them overcome those problems? Comments: Yes it is and only for a gold coin it’s a big help to the people of the community. Yes because we have played with it all before. Yes, I think it was very suitable. Yes, as they can ask anything they want. 5 x Yes!

How could this project have been improved? Comments: More sessions and more people volunteer to help. Longer sessions and more students to help More students, nothing else. Think if more help was given. Can’t think of anything wrong with the project. There isn’t anything that I can think of immediately. I think it’s great as it is now. I think it is great as it is. More people to be helped for better satisfaction in the community. It was very good already.

Appendix 4

## Older participants pre project

Albury Wodonga Volunteer Resource Bureau

Collated Survey results

45 participants – 45 responses

Tuesday 31st July, 7th Aug, 14th Aug 2012, Aug 21st, Aug 28th, Sept 4th, Sept 11th.

To help us with our reporting to Australian Communications Consumer Action Network Grants Scheme (ACCAN), the funding body that enabled this project to go ahead, please complete this survey.

- Why did you decide to participate in this project?

- 8 x To learn to use and iPad

- 2 x Learn/understand my computer

- To expand computer skill

- 2 x Learn more about my phone and laptop

- Learn to use my iPhone & iPad

- To be more confident in using my phone

- 2 x To be more comfortable with using the phone

- 2 x To learn how to operate my phone

- 2 x Need to learn how to effectively use new Smartphone

- I am so dumb with this phone!

- Unable to phone correctly

- Need to know an answer to a few technical features

- Learn something new

- I like it and keen to learn more

- Increase knowledge and to participate with the students being our volunteers

- To utilize my gizmos

- So I can learn more about technology

- To try and get into 20th Century & understand this technology

- 2 x Saw in local paper and was interested

- Friend

- I have no-one to show me how to work

- To be able to keep up with electronics world – no young children to help

- Ignorance

- Lack of knowledge

- Just a beginner

- Decide if I wish to purchase an iPad

- 2 x Get help

- What are your feelings about learning how to use new technology?

| Feelings about technology | Confident | Usually fine | Neutral | Bothers me | Fearful/avoid if possible |
| --- | --- | --- | --- | --- | --- |
| Number of responses | 3 | 18 | 8 | 12 | 3 |

- What do you hope to get out of this project?

- 5 x Knowledge of iPad

- Learn how to use iPad - email, internet

- Confidence to use iPad

- To learn how to use iphone/ipad more successfully

- Sending emails, using internet

- To be confident in using my phone

- Just to be able to use the mobile

- To be more competent with iphone

- Learn to operate smart phone

- Learn how to use phone with all its gadgets

- 2 x Learn more about my ipad & phone

- To learn how to use my phone so I can communicate & benefit from all its technology

- More skills on iphone & camera

- Use phone & computer

- To email a photo from ipad

- To be able to understand my gizmos and new technology

- 2 x Confidence in using the technology

- 3 x To be able to understand new technology

- Keeping up with progress (try0

- Better use of current technology

- 5 x More knowledge

- More computer knowledge

- More skills

- Better understanding

- Learn

- Practical usage ability

- Anything that will help

- Information

- A few technical problems – fixed

- Reduction in the occasional urge to destroy both gadgets (phone & laptop)

- When you bought your gizmo/s were you given adequate instructions?

| Response | Number of responses |
| --- | --- |
| YES | 7 |
| NO | 32 |

Comments:

- No but I find it hard to remember when I’m told

- Yes but I needed more help after purchase

- Sort of!

- Have you ever thrown away, given away or just not used a “gizmo” in frustration?

| Response | Number of responses |
| --- | --- |
| Yes | 12 |
| No | 29 |

Comments:

- 2 x Often

- Although hesitant and scared

- No – first adventure

- Have not used one before

- Not used gizmos to their full extent

- Yes. One  phone was too easy to press wrong buttons

- Yes – laptop computer – as hard to get a signal!

- Given it away because of lack of use

- Exercise machine – frustration not related to this technology

- How do you think you learn best? (Please circle all relevant)

| How you learn best | Listening | Reading | Hands on | Watching video | Watching others | All |
| --- | --- | --- | --- | --- | --- | --- |
| Number of responses | 12 | 11 | 41 | 2 | 8 | 1 |

- Circle any of the gizmos or communication methods with which you would like help.

| Gizmo or communication method | Number of responses |
| --- | --- |
| Mobile phone | 28 |
| iPad | 20 |
| Camera | 16 |
| Internet | 12 |
| Laptop | 11 |
| Skype | 8 |
| Navigation device | 7 |
| Facebook | 4 |
| Tweeting | 3 |
| Notebook | 1 |
| Car radio | 1 |

Appendix 5

## Older participants mid project

Collated results of mid project evaluation

28.08.12

Participants: (learners) 16 responses

- So far, how are you feeling about this project?

Circle the face or faces that show how you feel.

0 x Bored	    15 x Happy	                0 x Exhausted                0 x Disappointed                16 x Interested

- Is this project meeting your expectations?

- 16 x Yes

- Great thanks

- More

- A highlight so far?

- The students

- Downloads/Twitter

- Skype & Facebook registration

- Getting answers to my questions

- All concepts of re-learning the computer

- Finding all different apts

- Learnt about internet and favourites

- Learnt to clear apps, put on internet and download

- Being able to use my new touch phone with confidence

- Learning to use ipad camera with all its images

- Ipad skills

- Learnt a lot

- What I have learned.

- Understanding and learning

- Didn’t matter if you didn’t know anything – made welcome

- Have enjoyed and benefitted from students’ knowledge, patience and that of other participants.

- Any disappointments?

15 x No

Not sure of questions to ask

- Any other comments or suggestions?

- Albury High School students are excellent, happy and patient

- This course has been fantastic.  The students are very patient and understanding.

- I think the volunteers (all of them) are superb, knowledgeable and been of the utmost assistance.

- I think having the young students was an excellent idea and hope it continues to help others

- A joy to be part of this group.  Have learnt lots from other “students” and our clever young “teachers” get us through the technical hitch.

- Thank you to staff and students.  Wonderful concept! Real learning!! (

- Excellent teaching

- Great! When will the next classes start?

- Please run another class

- Run the classes again

- Program could continue

- An excellent programme.  Would like longer sessions.

- Everyone is very helpful and friendly

- Keep up good work

Appendix 6

## Older participants conclusion

Albury Wodonga Volunteer Resource Bureau

Collated results

18 attended final session – 18 responses

Participant survey – conclusion of project

To help us with our reporting to ACCAN the funding body that enabled this project to go ahead, please complete this survey.

| Have you learnt what you wanted to learn? Comments: I’m off to a great start with ipad and Apple phone. Great program Yes, though I missed sessions due to travel overseas. | 18 x YES | 0 x NO |
| --- | --- | --- |
| Are you using your gizmos more effectively? Comments: Heaps more | 18 x YES | 0 x NO |
| Which gizmos have you had help with during the project? 8 x Laptop 8 x ipad 8 x Phone 5 x camera 2 x GPS, Tom Tom Ipod Facebook Messaging |
| Did this arrangement (informal volunteer student tutoring) work for you? Comments: One to one attention appreciated. ?’s that I asked were answered. Yes, very relaxing and fun Very good arrangement Definitely Very well This is an excellent project. Yes, would like to see more of it. Yes, one on about one – you learn so much more | 18 x YES | 0 x NO |
| How was the experience of working with young students? e.g. Did they work at a pace that suited you? Did you get to know the students? Comments: Yes, really enjoyed the students’ commitment, help and knowledge. What a lovely group of students. Very polite and happy to help. Yes, they explained everything we needed to know. If they didn’t we worked well together to work it out. The student I worked with was most helpful and understanding. Excellent experience. Yes – suitable pace, Yes – got to know students. Yes the students coped very well with a lack of knowledge and endless questions. They were friendly, pleasant, tolerant and very knowledgeable about the ipad. The students were fantastic with their experience and patience. We got to know two of the students. Yes, we did get to know the students and they were very patient with us. They had plenty of patience. Students were very patient. We slowed them down after the first session. Great once they slowed to our pace. A terrific bunch of students. Yes, they were great to work with. Yes, very helpful. A great idea. Very good Very much so. |  |  |
| Were the facilities suitable? | 17 x YES | 0 x NO |
| Was the length of each session suitable? Comments: Could do even more! Session went very quickly | 17 x YES | 1 x NO |
| Was the number of sessions suitable? Comments: I missed a couple Could do with more! Perhaps 7 instead of 8 sessions | 16 x YES | 0 x NO |
| Were the numbers of students and participants suitable at all sessions? Comments: Some | 18 x YES | 0 x NO |
| Have there been any changes in your level of confidence regarding technology generally? Comments: 2 x I am much more confident. Not so afraid to have a go! Far more confident. | 17 x YES | 0 x NO |

| Are you using technology that is new to you as a result of this project? e.g. internet, online banking, Skype Comments: Not yet – Santa hopefully will bring me an ipad! Photos, email. Emailing of photos 2 x Internet, online banking | 15 x YES | 1 x NO |
| --- | --- | --- |
| As a result of this project will you feel more confident to purchase new gizmos? | 16 x YES | 1 x NO |
| Are you better informed to make decisions about new gizmos? Comments: Yes, a little more knowledgeable. Yes, much better informed. So long as I can come and get more lessons. | 16 x YES | 1 x NO |
| Was the information from guest speakers of value to you? Comment: Interesting Certainly, the policewoman was informative. Police lady very interesting I was away that day but brochures very helpful. | 15 x YES | 0 x NO |
| Would you participate in similar training? Comments: Different Yes, please contact me! Definitely. | 18 x YES | 0 x NO |
| Would you recommend this type of program to friends and family? Comments: I have been. Many friends very interested. Some don’t live locally but hope that this ‘project’ will travel. Locals hoping it will run again. Have told many friends, they are all keen. | 18 x YES | 0 x NO |
| How could this project have been improved? Comments: No improvement necessary – perhaps for it to be offered again in the same venue. No – very friendly! I think it was excellent, given it is a pilot, you got it right from the start!! Perhaps more one on one contact. Perhaps a student could be given an adult to instruct for the duration of the 8 weeks. Different students explain things in a different way which can be confusing. Because it is only for one hour there probably aren’t any changes that could make it any more effective. All excellent. Just increase frequency and content. More time, more sessions. |  |  |
| Any other comments: Well done all around, delightful students, pleasant staff, parking a wee bit tricky but would be very happy to come back again soon. A great program for oldies!! Camaraderie was excellent!! Because of the students, I am more confident with GIZMOS than before. A big thank you Thanks so much. Kids did a great job and to donate to a worthy cause is a credit to the “kids”. I would like to pass on to the school, a special thank you for allowing the students to participate in this project. Special thanks to Hudson and Daniel. A very worthwhile project. A great idea – hope it will continue – its benefit would be wide-spreading. Thank you so much – can’t say enough the info I have learnt Yes, please do it again. Many thanks Thank you very much More advertising is required for this course. |  |  |

# Appendix 7

## Staff/facilitator/teacher conclusion

Albury Wodonga Volunteer Resource Bureau

Collated results

18 attended final session – 18 responses

Participant survey – conclusion of project

To help us with our reporting to ACCAN the funding body that enabled this project to go ahead, please complete this survey.

| Have you learnt what you wanted to learn? Comments: I’m off to a great start with ipad and Apple phone. Great program Yes, though I missed sessions due to travel overseas. | 18 x YES | 0 x NO |
| --- | --- | --- |
| Are you using your gizmos more effectively? Comments: Heaps more | 18 x YES | 0 x NO |
| Which gizmos have you had help with during the project? 8 x Laptop 8 x ipad 8 x Phone 5 x camera 2 x GPS, Tom Tom Ipod Facebook Messaging |
| Did this arrangement (informal volunteer student tutoring) work for you? Comments: One to one attention appreciated. ?’s that I asked were answered. Yes, very relaxing and fun Very good arrangement Definitely Very well This is an excellent project. Yes, would like to see more of it. Yes, one on about one – you learn so much more | 18 x YES | 0 x NO |
| How was the experience of working with young students? e.g. Did they work at a pace that suited you? Did you get to know the students? Comments: Yes, really enjoyed the students’ commitment, help and knowledge. What a lovely group of students. Very polite and happy to help. Yes, they explained everything we needed to know. If they didn’t we worked well together to work it out. The student I worked with was most helpful and understanding. Excellent experience. Yes – suitable pace, Yes – got to know students. Yes the students coped very well with a lack of knowledge and endless questions. They were friendly, pleasant, tolerant and very knowledgeable about the ipad. The students were fantastic with their experience and patience. We got to know two of the students. Yes, we did get to know the students and they were very patient with us. They had plenty of patience. Students were very patient. We slowed them down after the first session. Great once they slowed to our pace. A terrific bunch of students. Yes, they were great to work with. Yes, very helpful. A great idea. Very good Very much so. |  |  |
| Were the facilities suitable? | 17 x YES | 0 x NO |
| Was the length of each session suitable? Comments: Could do even more! Session went very quickly | 17 x YES | 1 x NO |
| Was the number of sessions suitable? Comments: I missed a couple Could do with more! Perhaps 7 instead of 8 sessions | 16 x YES | 0 x NO |
| Were the numbers of students and participants suitable at all sessions? Comments: Some | 18 x YES | 0 x NO |
| Have there been any changes in your level of confidence regarding technology generally? Comments: 2 x I am much more confident. Not so afraid to have a go! Far more confident. | 17 x YES | 0 x NO |

| Are you using technology that is new to you as a result of this project? e.g. internet, online banking, Skype Comments: Not yet – Santa hopefully will bring me an ipad! Photos, email. Emailing of photos 2 x Internet, online banking | 15 x YES | 1 x NO |
| --- | --- | --- |
| As a result of this project will you feel more confident to purchase new gizmos? | 16 x YES | 1 x NO |
| Are you better informed to make decisions about new gizmos? Comments: Yes, a little more knowledgeable. Yes, much better informed. So long as I can come and get more lessons. | 16 x YES | 1 x NO |
| Was the information from guest speakers of value to you? Comment: Interesting Certainly, the policewoman was informative. Police lady very interesting I was away that day but brochures very helpful. | 15 x YES | 0 x NO |
| Would you participate in similar training? Comments: Different Yes, please contact me! Definitely. | 18 x YES | 0 x NO |
| Would you recommend this type of program to friends and family? Comments: I have been. Many friends very interested. Some don’t live locally but hope that this ‘project’ will travel. Locals hoping it will run again. Have told many friends, they are all keen. | 18 x YES | 0 x NO |
| How could this project have been improved? Comments: No improvement necessary – perhaps for it to be offered again in the same venue. No – very friendly! I think it was excellent, given it is a pilot, you got it right from the start!! Perhaps more one on one contact. Perhaps a student could be given an adult to instruct for the duration of the 8 weeks. Different students explain things in a different way which can be confusing. Because it is only for one hour there probably aren’t any changes that could make it any more effective. All excellent. Just increase frequency and content. More time, more sessions. |  |  |
| Any other comments: Well done all around, delightful students, pleasant staff, parking a wee bit tricky but would be very happy to come back again soon. A great program for oldies!! Camaraderie was excellent!! Because of the students, I am more confident with GIZMOS than before. A big thank you Thanks so much. Kids did a great job and to donate to a worthy cause is a credit to the “kids”. I would like to pass on to the school, a special thank you for allowing the students to participate in this project. Special thanks to Hudson and Daniel. A very worthwhile project. A great idea – hope it will continue – its benefit would be wide-spreading. Thank you so much – can’t say enough the info I have learnt Yes, please do it again. Many thanks Thank you very much More advertising is required for this course. |  |  |